## Project_Schedule
3CORE PORTAL — PROJECT IMPORT TEMPLATE
Fill rows 5-7 (column B and F) with project metadata, then list activities from row 12.
Project Name | Sandton Office Tower Refit |  |  | Total Budget (R) | 12500000
Project Number | STR-2026-007 |  |  | Start Date | 2026-06-01
Client | Liberty Holdings |  |  | Target End Date | 2027-05-31
# | Activity | Expected Output | Planned Start | Planned Finish | Budgeted Cost (R)
1 | Site Survey & Permits | Approved site survey and council permits | 2026-06-01 | 2026-06-30 | 450000
2 | Demolition - Floors 1-3 | Floors 1-3 stripped to slab; rubble removed | 2026-07-01 | 2026-08-15 | 1200000
3 | Demolition - Floors 4-6 | Floors 4-6 stripped to slab; rubble removed | 2026-08-01 | 2026-09-15 | 1200000
4 | Structural Reinforcement | All floors reinforced to spec; inspection passed | 2026-09-16 | 2026-11-30 | 2400000
5 | MEP First Fix | Electrical/plumbing/HVAC roughed in across floors | 2026-11-01 | 2027-01-31 | 1800000
6 | Partitions & Drywall | Internal partition walls installed and skimmed | 2027-01-15 | 2027-02-28 | 900000
7 | Flooring & Finishes | All flooring laid; ceilings installed | 2027-02-15 | 2027-03-31 | 1400000
8 | MEP Second Fix & Commission | Fixtures installed; systems commissioned | 2027-03-01 | 2027-04-15 | 1100000
9 | Painting & Joinery | All paint and built-in joinery complete | 2027-04-01 | 2027-05-10 | 650000
10 | Snag List & Handover | Snags closed; client handover document signed | 2027-05-11 | 2027-05-31 | 400000